## Instructions
INSTRUCTIONS
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Parties: Lumbee Tribe of North Carolina (the “Tribe”) and LREMC Technologies, LLC d/b/a RIVR Tech (“RIVR Tech”)
Exhibit D — Construction Milestones
Purpose: sequence the buildout, tie milestones to payment/triggers and grant reporting, and enforce that no construction begins before environmental clearance and NTIA authorization to construct.
Hard sequencing rule
• NO CONSTRUCTION may begin before NEPA/NHPA environmental clearance and NTIA authorization to construct are obtained.
• National Environmental Policy Act (NEPA), 42 U.S.C. § 4321 et seq., and DOC/NTIA implementing procedures
• National Historic Preservation Act § 106, 54 U.S.C. § 306108 (36 CFR Part 800)
How to use
• AMBER cells are inputs — enter dates and % complete.
• The CHECK column verifies Planned Finish >= Planned Start for each milestone.
• Enter dates as real Excel dates so the checks evaluate numerically.
Status
• DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Milestones
EXHIBIT D — CONSTRUCTION MILESTONES
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Environmental clearance and NTIA authorization gate all construction
Milestone # | Description | Predecessor | Planned Start | Planned Finish | % Complete | Payment / Trigger | Grant Reporting Tie | Finish>=Start (check)
M1 | NEPA/NHPA environmental clearance AND NTIA authorization to construct (GATE — no construction before this milestone) | — | [■ start date] | [■ finish date] | [■ %] | Env. review complete; ATC issued | NTIA authorization to construct; environmental determination on file
M2 | Permitting, easements, pole-attachment agreements, and 811 locates | M1 | [■ start date] | [■ finish date] | [■ %] | Right-of-way secured | Permit/easement package to grant file
M3 | Material procurement (BABA-compliant; §889 screening) | M1 | [■ start date] | [■ finish date] | [■ %] | PO issuance / material delivery | BABA compliance certification; Buy-America documentation
M4 | Outside-plant (OSP) construction — conduit, fiber placement | M2, M3 | [■ start date] | [■ finish date] | [■ %] | Progress draw(s) by route segment | Construction progress / disbursement report
M5 | Splicing and termination | M4 | [■ start date] | [■ finish date] | [■ %] | Splice completion by segment | As-built splice records
M6 | Electronics installation (OLTs, aggregation, core interconnect) | M4 | [■ start date] | [■ finish date] | [■ %] | Equipment acceptance | Equipment inventory update (Exhibit K)
M7 | Testing and acceptance (Exhibit E standards) | M5, M6 | [■ start date] | [■ finish date] | [■ %] | Acceptance certificate (Exhibit G) | Acceptance test results filed
M8 | Service activation / place in service | M7 | [■ start date] | [■ finish date] | [■ %] | First subscribers; in-service date set | Place-in-service date (federal-interest / depreciation)
M9 | Buildout complete / project closeout readiness | M8 | [■ start date] | [■ finish date] | [■ %] | Final draw / retainage release | Closeout package — 2 CFR 200.344 (Closeout) and 2 CFR 200.345 (Post-closeout adjustments and continuing responsibilities)
Gate & rollup checks
Environmental/authorization gate (M1) is scheduled first:
Average % complete across milestones: