## Instructions
INSTRUCTIONS
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Parties: Lumbee Tribe of North Carolina (the “Tribe”) and LREMC Technologies, LLC d/b/a RIVR Tech (“RIVR Tech”)
Exhibit L — Responsibility (RACI) Matrix
Purpose: assign Responsible / Accountable / Consulted / Informed for each activity across the Tribe, RIVR Tech, Grant Counsel, and NTIA.
RACI legend
• R = Responsible (does the work)
• A = Accountable (owns the outcome — exactly one per row)
• C = Consulted (two-way input)
• I = Informed (kept up to date)
How to use
• Each activity cell has a dropdown limited to R, A, C, or I.
• Confirm exactly one 'A' per row.
Status
• DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## RACI
EXHIBIT L — RESPONSIBILITY (RACI) MATRIX
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
R = Responsible · A = Accountable · C = Consulted · I = Informed
Activity | Tribe | RIVR Tech | Grant Counsel | NTIA
Grant application & award management | A | C | C | I
Network design / engineering | C | A | I | I
Environmental review (NEPA/NHPA) | A | C | C | A
Permitting & easements | C | A | C | I
Procurement (incl. BABA / §889) | A | R | C | I
Construction | I | A | I | I
Testing & acceptance | A | R | I | I
Asset & property records (2 CFR 200.313) | A | C | C | I
Network operations | I | A | I | I
Billing & collections | I | A | I | I
Customer service | C | A | I | I
Marketing & outreach | C | A | I | I
Regulatory compliance (FCC/NTIA) | A | R | C | I
Grant reporting | A | C | C | I
Audit (single audit / program) | A | C | C | I
Maintenance & repair | I | A | I | I
Capital replacement / renewal | A | C | C | I
Cybersecurity | C | A | C | I
Step-in / continuity of essential services | A | R | C | I
Asset disposition (2 CFR 200.313) | A | C | C | A
Accountability checks (exactly one 'A' per row)
Row 6:
Row 7:
Row 8:
Row 9:
Row 10:
Row 11:
Row 12:
Row 13:
Row 14:
Row 15:
Row 16:
Row 17:
Row 18:
Row 19:
Row 20:
Row 21:
Row 22:
Row 23:
Row 24:
Row 25: