## Instructions
INSTRUCTIONS
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Parties: Lumbee Tribe of North Carolina (the “Tribe”) and LREMC Technologies, LLC d/b/a RIVR Tech (“RIVR Tech”)
Negotiation Risk Matrix
Scores each material risk in the Lumbee Tribe / RIVR Tech transaction. Score = Likelihood x Impact (each 1–5, so 1–25).
• Enter Likelihood and Impact (amber input cells, 1–5). Score is a formula (blue) and auto-highlights: red when >= 15 (high), amber 8–14 (medium), green <= 7 (low).
• Likelihood/Impact scale: 1 = very low, 3 = moderate, 5 = very high.
• Mitigation and Owner columns capture the plan and accountable party.
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Risk Matrix
Negotiation Risk Matrix
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Likelihood x Impact scoring — draft for counsel and business review
Risk | Category | Likelihood (1-5) | Impact (1-5) | Score (=LxI) | Mitigation | Owner
Lumbee federal recognition / TBCP eligibility | Grant / Threshold | 3 | 5 |  | Confirm eligibility with NTIA in writing before acceptance; fallback eligible designated entity; condition agreements on confirmation. | Tribal + Grant counsel
Grant clawback / recapture | Grant | 3 | 5 |  | Fault-based allocation; RIVR indemnity for operator-caused noncompliance; compliance reserve; strict property/disposition controls. | Grant counsel + Finance
Construction cost overrun | Construction / Financial | 4 | 4 |  | GMP/fixed-price where possible; contingency; change-order controls; performance/payment bonds. | RIVR + Finance
Take-rate / adoption shortfall | Commercial | 4 | 4 |  | Conservative model; affordability tier + marketing plan; revenue-share sized to downside; milestone-based obligations. | Business + Finance
Sovereign-immunity impasse | Legal | 3 | 4 |  | Early principled negotiation; limited express waiver for arbitration only; asset-limited caps; separate Council action. | Both parties' counsel
Environmental / historic-review delay | Regulatory | 3 | 3 |  | Start NEPA/NHPA §106 early; route around sensitive sites; schedule float; SHPO/THPO consultation. | Grant counsel + RIVR
BABA sourcing non-compliance / delay | Grant / Supply | 3 | 4 |  | Early BABA-compliant sourcing; supplier certifications; waiver process if needed; document domestic content. | RIVR + Grant counsel
Program-income treatment dispute | Grant / Financial | 3 | 3 |  | Confirm method with NTIA up front; structure revenue-share to satisfy 200.307; document in financial schedule. | Grant counsel + Finance
Impermissible private benefit | Grant | 2 | 5 |  | Fair, benchmarked, documented consideration to Tribe; public-purpose protections; reversion; arm's-length terms. | Grant counsel + Finance
Operator default / step-in event | Operational / Legal | 2 | 5 |  | Clear default/cure; Tribe emergency step-in; replacement-operator plan; escrow of records/credentials. | Tribal counsel + RIVR
Asset encumbrance conflict with federal interest | Grant / Legal | 3 | 4 |  | No liens on Tribal Assets; confirm IRU is permissible use; security from RIVR assets only; NTIA position letter. | Grant + Tribal counsel
Easement / ROW / pole-attachment failure | Real Estate | 3 | 3 |  | Secure recordable long-duration easements/ROW; pole agreements; allocate permitting risk; survival on transition. | Real-estate counsel + RIVR
Governing-law / jurisdiction dispute | Legal | 2 | 4 |  | Resolve choice-of-law + forum + exhaustion together; consistent across the agreement suite. | Both parties' counsel
Regulatory / ETC / USAC compliance gap | Regulatory | 2 | 3 |  | RIVR holds carrier authorizations/ETC; assign CPNI; compliance calendar. | Regulatory counsel + RIVR
Insurance / bonding inadequacy | Risk | 2 | 3 |  | Enforce Exhibit I limits; additional-insured/waiver of subrogation; annual COI verification. | Risk + RIVR
Transition / end-of-term service disruption | Operational | 2 | 4 |  | 12-mo transition assistance; records/customer handover; defined transition pricing; step-in fallback. | Both parties + Business
Cybersecurity / data breach (CPNI) | Operational / Privacy | 2 | 4 |  | Cyber insurance ($5M); CPNI/privacy controls; incident response; §889 equipment ban compliance. | RIVR + Privacy counsel
Score bands: | High (>=15) | Medium (8-14) | Low (<=7)