## Instructions
Instructions
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Procurement and OCI Checklist — Phase 1 Diligence
Document 05 of the Phase 1 Diligence set.
No executed TBCP award, CD-450 Financial Assistance Award, Notice of Funding Opportunity PDF, Specific Award Conditions, Tribal resolution, title/easement record, or existing RIVR Tech / LREMC contract was supplied for this work product. All conclusions are provisional and keyed to the assumptions register in Document 01.
How to use
• Sheet 'Procurement' documents how RIVR Tech's selection must be supported under 2 CFR 200.317–200.327 (Procurement standards).
• Sheet 'OCI & Conduct' covers organizational conflict of interest and standards of conduct under 2 CFR 200.318(c)(1)-(2) (organizational conflict of interest and written standards of conduct).
• Because RIVR Tech (LREMC Technologies, LLC) is affiliated with LREMC, the OCI/standards-of-conduct analysis is critical.
• Status: OPEN = not yet evidenced; IN PROGRESS; SATISFIED. Fill Evidence/Doc and Owner as records arrive.
• Nearly all rows are OPEN because no procurement record was supplied - do not invent one.
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Procurement
Procurement Compliance Checklist (2 CFR 200.317-200.327)
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Documents how RIVR Tech's selection must be supported; nearly all rows OPEN (no record supplied).
Requirement | Citation | Status | Evidence/Doc | Owner
General procurement standards
Documented procurement procedures consistent with federal standards | 2 CFR 200.317–200.327 (Procurement standards) | OPEN | [■ procedures] | Lumbee Tribe
Written standards of conduct / conflict-of-interest policy in force | 2 CFR 200.318(c) and 2 CFR 200.112 (Conflict of interest) | OPEN | [■ policy] | Lumbee Tribe
Necessity / avoidance of unnecessary or duplicative purchases | 2 CFR 200.318(d) | OPEN | [■ analysis] | Lumbee Tribe
Competition
Full and open competition; no unfair advantage to affiliates | 2 CFR 200.319 (Competition) | OPEN | [■ solicitation] | Lumbee Tribe
No restrictive specifications or geographic preferences (except as allowed) | 2 CFR 200.319 (Competition) | OPEN | [■ spec review] | Lumbee Tribe
Solicitation clearly describes requirements and evaluation basis | 2 CFR 200.319(c) | OPEN | [■ solicitation] | Lumbee Tribe
Methods of procurement
Method selected and documented (small purchase / sealed bid / proposals) | 2 CFR 200.320 (Methods of procurement) | OPEN | [■ method memo] | Lumbee Tribe
If noncompetitive/sole-source: written justification meets a 200.320(c) exception | 2 CFR 200.320(c) | OPEN | [■ sole-source justification] | Lumbee Tribe
Sole-source exception analysis (unique source / urgency / competition inadequate / awarding-agency authorization) | 2 CFR 200.320(c)(1)-(4) | OPEN | [■ exception analysis] | Lumbee Tribe
Cost / price and contractor responsibility
Cost or price analysis performed and documented | 2 CFR 200.324 | OPEN | [■ cost/price analysis] | Lumbee Tribe
Contractor responsibility determination (integrity, capacity, record) | 2 CFR 200.318(h) | OPEN | [■ responsibility memo] | Lumbee Tribe
Debarment / suspension (SAM exclusions) verification | 2 CFR Part 180 and 2 CFR Part 1327 (Governmentwide debarment and suspension — DOC/NTIA adoption) | OPEN | [■ SAM check] | Lumbee Tribe
Required contract provisions and preferences
Required contract clauses included (Appendix II to Part 200) | 2 CFR Part 200, Appendix II | OPEN | [■ clause matrix] | Lumbee Tribe
Domestic preference / BABA compliance addressed | 2 CFR 200.322 (Domestic preferences for procurements); Build America, Buy America Act, IIJA §§ 70911–70917 (Pub. L. 117-58); 2 CFR Part 184; and NTIA BABA award terms | OPEN | [■ BABA record] | RIVR Tech
Section 889 covered-equipment prohibition addressed | 2 CFR 200.216 (Prohibition on certain telecommunications and video surveillance — §889 covered equipment) | OPEN | [■ 889 attestation] | RIVR Tech
Procurement records retained and available for access | 2 CFR 200.334–200.337 (Record retention and access; three-year retention) | OPEN | [■ record file] | Lumbee Tribe
Approvals
Awarding-agency pre-procurement review, if required | 2 CFR 200.325 | OPEN | [■ agency review] | Lumbee Tribe
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## OCI & Conduct
Organizational Conflict of Interest & Standards of Conduct
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Critical because RIVR Tech (LREMC Technologies, LLC) is affiliated with LREMC, a separate asset owner.
Requirement | Citation | Status | Evidence/Doc | Owner
Organizational conflict of interest
Identify affiliation between RIVR Tech, LREMC Technologies LLC, and LREMC | 2 CFR 200.318(c)(1)-(2) (organizational conflict of interest and written standards of conduct) | OPEN | [■ org chart / ownership] | RIVR Tech
Assess OCI arising from affiliate ownership of poles/fiber/easements/land | 2 CFR 200.318(c)(1)-(2) (organizational conflict of interest and written standards of conduct) | OPEN | [■ OCI assessment] | Lumbee Tribe
Mitigation plan for identified OCI (firewalls, disclosures, recusal) | 2 CFR 200.318(c)(1)-(2) (organizational conflict of interest and written standards of conduct) | OPEN | [■ mitigation plan] | Lumbee Tribe
Standards of conduct / individual conflicts
Written standards of conduct covering employees/officers/agents | 2 CFR 200.318(c) and 2 CFR 200.112 (Conflict of interest) | OPEN | [■ policy] | Lumbee Tribe
No employee with a real/apparent conflict participates in selection | 2 CFR 200.318(c) and 2 CFR 200.112 (Conflict of interest) | OPEN | [■ recusal record] | Lumbee Tribe
Gifts/gratuities prohibition and disciplinary provisions | 2 CFR 200.318(c)(1) | OPEN | [■ policy] | Lumbee Tribe
Mandatory disclosure of violations of law/fraud | 2 CFR 200.113 (Mandatory disclosures) | OPEN | [■ disclosure procedure] | Lumbee Tribe
Related-party economics
Arm's-length pricing for any LREMC-owned facilities used | 2 CFR Part 200, Subpart E (Cost Principles — allowability, allocability, reasonableness) | OPEN | [■ pricing basis] | RIVR Tech
Consideration/valuation for existing RIVR Tech assets (never free) | 2 CFR Part 200, Subpart E (Cost Principles — allowability, allocability, reasonableness) | OPEN | [■ valuation] | RIVR Tech
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT