## Instructions
INSTRUCTIONS
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Closing Checklist
Conditions to signing/closing the Lumbee Tribe / RIVR Tech broadband transaction. Status dropdown: Not Started / In Progress / Complete / Waived / N/A.
• Assign Responsible and record the executed Doc Ref for each item.
• Authorizations (05_Authorizations) and review materials (06_Review_Materials) feed this list.
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Closing Checklist
Closing Checklist
DRAFT FOR DISCUSSION – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Conditions to execution / closing — draft for counsel review
Item | Category | Responsible | Status | Doc Ref | Notes
TBCP eligibility confirmation obtained | Threshold / Grant | Tribal + Grant counsel | Not Started | [■ NTIA letter] | Gating
TBCP award accepted / award documents signed | Grant | Tribe | Not Started | [■ signed award] | If awarded
Lumbee Tribal Council resolution adopted | Authorization | Tribe | Not Started | 05.01 | This package
RIVR Tech corporate authorization executed | Authorization | RIVR | Not Started | 05.02 | This package
Certificates of authority / incumbency (both) | Authorization | Both | Not Started | 05.03 | This package
Master Development, Construction & Operating Agreement executed | Agreement | Both | Not Started | 02.01
IRU Agreement executed | Agreement | Both | Not Started | 02.02 | Term confirmed
O&M / SLA schedule finalized & executed | Agreement | Both | Not Started | 02.03
Financial schedule finalized & executed | Agreement | Both | Not Started | 02.04 | Economics confirmed
Grant-compliance agreement executed | Agreement | Both | Not Started | 02.05
Privacy / data agreement executed | Agreement | Both | Not Started | 02.06 | CPNI
Transition agreement executed | Agreement | Both | Not Started | 02.07
Exhibits finalized (fiber, network, insurance, maps) | Exhibits | Both | Not Started | [■ exhibit set] | Incl. Exhibit I
Insurance certificates delivered | Risk | RIVR | Not Started | [■ COIs] | Additional insured
Performance / payment bonds delivered | Risk | RIVR | Not Started | [■ bonds] | Construction
NTIA approvals / consents (as required) | Grant | Grant counsel | Not Started | [■ consents] | If required
BIA / land-status approvals (if applicable) | Regulatory | Tribal counsel | Not Started | [■ BIA consent] | May be N/A
Environmental / NHPA clearance | Regulatory | Grant counsel | Not Started | [■ clearances]
Easements / rights-of-way secured | Real Estate | Real-estate counsel | Not Started | [■ recorded easements]
Pole-attachment agreements in place | Real Estate | RIVR | Not Started | [■ pole agreements]
Legal opinion letters delivered | Legal | Both counsel | Not Started | [■ opinions] | Authority / enforceability
Good-standing certificates (both entities) | Legal | Both | Not Started | [■ good-standing]
Sovereign-immunity / dispute-resolution terms resolved | Legal | Both counsel | Not Started | [■ final clause] | Separate Council action
Regulatory authorizations / ETC status confirmed | Regulatory | Regulatory counsel | Not Started | [■ authorizations]
Funds-flow / accounts established | Financial | Finance | Not Started | [■ account setup] | Program income