## Instructions
INSTRUCTIONS
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Parties: Lumbee Tribe of North Carolina (the “Lumbee Tribe”); LREMC Technologies, LLC d/b/a RIVR Tech (“RIVR Tech”); Lumbee River Electric Membership Corporation d/b/a Lumbee River EMC (“LREMC”), separate asset owner.
Program Checklists
Five program checklists spanning the transaction lifecycle for the TBCP project.
• Each sheet has frozen, filterable headers and a Status dropdown (Not Started / In Progress / Complete / N/A).
• Amber INPUT columns (Status / Doc Ref / Notes) are yours to complete.
• Cross-references: the Definitive Agreements and Schedules S1–S14.
• PRELIMINARY DRAFT – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Closing Checklist
Closing Checklist
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Conditions to closing the coordinated TBCP transaction
Item | Responsible | Status | Doc Ref | Notes
Executed federal Award confirmed (controlling round / FAIN) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Master TBCP Partnership and Implementation Agreement executed | Both Parties | [■ status] | [■ doc ref] | [■ notes]
All Definitive Agreements executed | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Tribal Council resolutions / authorizations | Lumbee Tribe | [■ status] | [■ doc ref] | [■ notes]
Corporate authorizations (RIVR Tech / LREMC) | RIVR Tech / LREMC | [■ status] | [■ doc ref] | [■ notes]
Document-precedence schedule (S1) finalized | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Land / easement / ROW instruments recorded (S9) | Lumbee Tribe / LREMC | [■ status] | [■ doc ref] | [■ notes]
BIA approvals for trust / restricted land (25 CFR 162/169) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Insurance certificates in force (Exhibit I limits) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Lender consents obtained (if financed assets) | RIVR Tech / LREMC | [■ status] | [■ doc ref] | [■ notes]
NTIA consent to IRU / operating arrangement | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
§889 / covered-telecom certifications (2 CFR 200.216 (Prohibition on certain telecommunications and video surveillance — §889 covered equipment)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
SAM.gov registration active | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Conflict-of-interest disclosures (2 CFR 200.318(c) and 2 CFR 200.112 (Conflict of interest)) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
All items Complete or N/A:

## Construction-Release
Construction-Release Checklist
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Conditions to releasing construction (per segment)
Item | Responsible | Status | Doc Ref | Notes
Notice to Proceed issued (Form 1.1) | RIVR Tech PM | [■ status] | [■ doc ref] | [■ notes]
NEPA environmental review complete (National Environmental Policy Act (NEPA), 42 U.S.C. § 4321 et seq., and DOC/NTIA implementing procedures) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
NHPA §106 review complete (National Historic Preservation Act § 106, 54 U.S.C. § 306108 (36 CFR Part 800)) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Permits obtained (NCDOT / encroachment — N.C. Gen. Stat. § 136-18 and NCDOT utility accommodation policy (encroachment/ROW in NCDOT corridors)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Pole attachment authorizations (N.C. Gen. Stat. § 62-350 (broadband attachment to utility poles)) | RIVR Tech / LREMC | [■ status] | [■ doc ref] | [■ notes]
811 utility locates complete (N.C. Gen. Stat. Ch. 87, Art. 8A (Underground Utility Safety and Damage Prevention Act / 811 locates)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
BABA compliance plan in place (Build America, Buy America Act, IIJA §§ 70911–70917 (Pub. L. 117-58); 2 CFR Part 184; and NTIA BABA award terms) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Procurement performed per 2 CFR 200.317–200.327 (Procurement standards) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Bill of materials / engineering approved (S4) | Lumbee Tribe / RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Construction pricing / milestones set (S5) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Builders-risk / construction insurance in force | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Site safety plan in place | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
All items Complete or N/A:

## Service-Launch
Service-Launch Checklist
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Conditions to launching retail service on a segment
Item | Responsible | Status | Doc Ref | Notes
Segment Acceptance Form executed (Form 1.9) | Lumbee Tribe / RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
OTDR / optical test results on file (bi-directional OTDR) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Segment IRU Activation Certificate executed (Form 02) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Retail provider-of-record readiness (S7) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Billing / collections system live | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Affordability program enrollment (Lifeline/ETC — 47 CFR Part 54 (USAC/FCC universal service, Lifeline, and ETC requirements)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Subscriber onboarding process ready | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
NOC 24x7x365 monitoring live | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
SLA monitoring & reporting configured (S6) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
CPNI / privacy controls in place (47 U.S.C. § 222 and 47 CFR §§ 64.2001–64.2011 (Customer Proprietary Network Information)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Data privacy & cybersecurity addendum in effect (S11) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Subscriber payment / reconciliation process ready (S8) | RIVR Tech / Lumbee Tribe | [■ status] | [■ doc ref] | [■ notes]
All items Complete or N/A:

## Annual-Compliance
Annual-Compliance Checklist
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Recurring annual compliance obligations
Item | Responsible | Status | Doc Ref | Notes
Single audit filed if expenditures ≥ $1,000,000 (2 CFR Part 200, Subpart F (Audit Requirements; single-audit threshold $1,000,000)) | Lumbee Tribe / Auditor | [■ status] | [■ doc ref] | [■ notes]
Performance & financial reports to NTIA | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Program-income reporting (2 CFR 200.307 (Program income)) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Asset / property register updated (2 CFR 200.313 (Equipment — use, management, and disposition)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Federal-Interest register reconciled (2 CFR 200.316 (Property trust relationship)) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Reimbursement records retained (2 CFR 200.334–200.337 (Record retention and access; three-year retention)) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
BABA ongoing compliance confirmed | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
§889 re-certification (2 CFR 200.216 (Prohibition on certain telecommunications and video surveillance — §889 covered equipment)) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Insurance renewals confirmed | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
SLA performance review (S6) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Replacement-reserve funding reviewed (S6) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Conflict-of-interest annual disclosures (2 CFR 200.318(c) and 2 CFR 200.112 (Conflict of interest)) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Annual budget / sustainability review completed (Form 05) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
All items Complete or N/A:

## Termination-Transition
Termination / Transition Checklist
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Steps on default, termination, or transition of operations
Item | Responsible | Status | Doc Ref | Notes
Default / cure status determined (cure: 30d monetary / 60d non-monetary) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Step-in triggers assessed (immediate, upon notice, where continuity…) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
Transition-assistance plan activated (12 months) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Records & asset transfer to Lumbee Tribe | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Software / license assignment (assignable licenses) | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
Subscriber notification & continuity | RIVR Tech | [■ status] | [■ doc ref] | [■ notes]
NTIA notification of transition / termination | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Federal-interest disposition (2 CFR 200.311 (Real property — use, encumbrance, and disposition); 2 CFR 200.316 (Property trust relationship)) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Award closeout (2 CFR 200.344 (Closeout) and 2 CFR 200.345 (Post-closeout adjustments and continuing responsibilities)) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Post-closeout obligations acknowledged (200.345) | Grant Counsel | [■ status] | [■ doc ref] | [■ notes]
Lien releases / lender payoff (if any) | RIVR Tech / LREMC | [■ status] | [■ doc ref] | [■ notes]
Final reconciliation & payment (Form 04) | Both Parties | [■ status] | [■ doc ref] | [■ notes]
All items Complete or N/A: