## Instructions
Compliance Crosswalk
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Parties: Lumbee Tribe of North Carolina (the “Lumbee Tribe”); LREMC Technologies, LLC d/b/a RIVR Tech (“RIVR Tech”); Lumbee River Electric Membership Corporation d/b/a Lumbee River EMC (“LREMC”), separate asset owner.
Clause-by-Clause Compliance Crosswalk
This workbook maps each federal compliance requirement to its controlling authority, where it is addressed in the package, its rule type, current status, and notes.
How to use
• Filter the header row to focus on OPEN items or a single rule type.
• The 'Where Addressed' column points to the governing agreement and Schedule(s).
• The 'Type' column classifies each requirement as Mandatory / Interpretation / Recommended / Negotiable.
• Status values: OPEN, IN PROGRESS, ADDRESSED, N/A.
Reliance limits
• PRELIMINARY: no controlling award or source documents were supplied.
• Provisional baseline is the March 2024 amended Round 2 NOFO; Round 3 is live and must be confirmed.
• Citations are drawn from the canonical citation table; confirm against the executed award.
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Crosswalk
Clause-by-Clause Compliance Crosswalk
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Lumbee Tribe / RIVR Tech TBCP fiber package — Preliminary Draft v0.1
Requirement | Controlling Authority | Where Addressed (Agreement / Schedule) | Type | Status | Notes
Recipient / entity eligibility (Tribal recognition) | Lumbee Act of 1956, Pub. L. 84-570, 70 Stat. 254 (federal-recognition status affecting TBCP eligibility) | Master TBCP Partnership and Implementation Agreement; S1/S14; Eligibility Opinion | Mandatory | OPEN | [GRANT COMPLIANCE REVIEW REQUIRED] [ATTORNEY REVIEW REQUIRED] Threshold eligibility; confirm before reliance.
Real property use, encumbrance, disposition; property trust | 2 CFR 200.311 (Real property — use, encumbrance, and disposition); 2 CFR 200.316 (Property trust relationship) | Indefeasible Right of Use and Network Access Agreement; Land, Easement, Right-of-Way, Pole, Site, Power, and Facility Instruments; S3/S9 | Mandatory | OPEN | Federal Interest limits on encumbrance/disposition must flow into IRU and land instruments.
Equipment management, records, and disposition (200.313(d)) | 2 CFR 200.313 (Equipment — use, management, and disposition) | Network Operations, Maintenance, and Lifecycle Agreement; Grant Finance, Reimbursement, Program Income, and Audit Agreement; S3/S6 | Mandatory | OPEN | Property records, physical inventory, control, and disposition procedures required.
Procurement standards, competition, methods | 2 CFR 200.317–200.327 (Procurement standards); 2 CFR 200.319 (Competition); 2 CFR 200.320 (Methods of procurement) | Design, Engineering, Procurement, and Construction Agreement; Grant Finance, Reimbursement, Program Income, and Audit Agreement; S5 | Mandatory | OPEN | [GRANT COMPLIANCE REVIEW REQUIRED] Confirm procurement record supports the DEPC pricing.
Contractor vs. subrecipient determination; pass-through duties | 2 CFR 200.331 (Subrecipient and contractor determinations); 2 CFR 200.332 (Requirements for pass-through entities) | Master TBCP Partnership and Implementation Agreement; Grant Finance, Reimbursement, Program Income, and Audit Agreement; S1 | Mandatory | OPEN | [GRANT COMPLIANCE REVIEW REQUIRED] Position RIVR Tech as lean contractor; substance-over-form.
Program income | 2 CFR 200.307 (Program income) | Retail Customer Service, Billing, Collections, and Subscriber Revenue Agreement; Grant Finance, Reimbursement, Program Income, and Audit Agreement; S8 | Interpretation | OPEN | characterization is provisional; program-income treatment under 2 CFR 200.307 turns on the controlling Award and written NTIA determination, not the label.
Build America, Buy America (domestic content) | Build America, Buy America Act, IIJA §§ 70911–70917 (Pub. L. 117-58); 2 CFR Part 184; and NTIA BABA award terms | Design, Engineering, Procurement, and Construction Agreement; S4/S5 | Mandatory | OPEN | Iron/steel, manufactured products, construction materials; certifications required.
Prohibited telecommunications equipment (§889 covered) | 2 CFR 200.216 (Prohibition on certain telecommunications and video surveillance — §889 covered equipment) | Design, Engineering, Procurement, and Construction Agreement; Data Privacy, Cybersecurity, Supply-Chain Risk, and Business Continuity Addendum; S4/S11 | Mandatory | OPEN | Vendor screening and certifications; no covered equipment/services.
NEPA environmental review | National Environmental Policy Act (NEPA), 42 U.S.C. § 4321 et seq., and DOC/NTIA implementing procedures | Master TBCP Partnership and Implementation Agreement; Design, Engineering, Procurement, and Construction Agreement; S2/S9 | Mandatory | OPEN | Complete before ground-disturbing construction / NTP.
NHPA Section 106 historic-preservation review | National Historic Preservation Act § 106, 54 U.S.C. § 306108 (36 CFR Part 800) | Design, Engineering, Procurement, and Construction Agreement; Land, Easement, Right-of-Way, Pole, Site, Power, and Facility Instruments; S9 | Mandatory | OPEN | Tribal/SHPO consultation; complete before NTP.
Record retention and access (3 years) | 2 CFR 200.334–200.337 (Record retention and access; three-year retention) | Grant Finance, Reimbursement, Program Income, and Audit Agreement; all agreements; S8 | Mandatory | OPEN | Retention measured from final report; access for auditors.
Single audit (Subpart F) | 2 CFR Part 200, Subpart F (Audit Requirements; single-audit threshold $1,000,000) | Grant Finance, Reimbursement, Program Income, and Audit Agreement; S8 | Mandatory | OPEN | Applies at/above the $1,000,000 federal-award expenditure threshold.
Property disposition on termination/closeout | 2 CFR 200.311 (Real property — use, encumbrance, and disposition); 2 CFR 200.313 (Equipment — use, management, and disposition) | Indefeasible Right of Use and Network Access Agreement; Network Operations, Maintenance, and Lifecycle Agreement; Continuity, Step-In, Termination Assistance, and Transition Agreement; S3/S13 | Mandatory | OPEN | Disposition instructions per Federal Interest; step-in continuity.
Cost principles (allowability/allocability/reasonableness) | 2 CFR Part 200, Subpart E (Cost Principles — allowability, allocability, reasonableness) | Grant Finance, Reimbursement, Program Income, and Audit Agreement; Design, Engineering, Procurement, and Construction Agreement; S5/S8 | Mandatory | OPEN | Costs charged to the award must satisfy Subpart E.
Domestic preferences for procurements | 2 CFR 200.322 (Domestic preferences for procurements) | Design, Engineering, Procurement, and Construction Agreement; S5 | Recommended | OPEN | Preference for domestic goods/services to the extent practicable.
Conflict of interest / standards of conduct | 2 CFR 200.318(c) and 2 CFR 200.112 (Conflict of interest); 2 CFR 200.318(c)(1)-(2) (organizational conflict of interest and written standards of conduct) | Master TBCP Partnership and Implementation Agreement; Governance; S1 | Mandatory | OPEN | Written standards of conduct; organizational COI screening (LREMC affiliation).
Remedies for noncompliance; termination | 2 CFR 200.339–200.343 (Remedies for noncompliance; termination) | Master TBCP Partnership and Implementation Agreement; Continuity, Step-In, Termination Assistance, and Transition Agreement; S13 | Mandatory | OPEN | Enforcement, disallowance, suspension, termination pathways.
Closeout and post-closeout adjustments | 2 CFR 200.344 (Closeout) and 2 CFR 200.345 (Post-closeout adjustments and continuing responsibilities) | Grant Finance, Reimbursement, Program Income, and Audit Agreement; Continuity, Step-In, Termination Assistance, and Transition Agreement; S8/S13 | Mandatory | OPEN | Final reports, liquidation, continuing obligations.
Affordability and 100/20 Mbps service floor | TBCP NOFO / ID Guidance; 47 CFR Part 54 (USAC/FCC universal service, Lifeline, and ETC requirements) | Retail Customer Service, Billing, Collections, and Subscriber Revenue Agreement; S7 | Mandatory | OPEN | Service floor 100/20 Mbps; affordability commitments per award.
Open, nondiscriminatory middle-mile interconnection | TBCP Round 2 Notice of Funding Opportunity, as amended March 2024 (PROVISIONAL BASELINE — controlling round/award NOT supplied; confirm before finalizing); TBCP Infrastructure Deployment Application Guidance (NTIA) — confirm the version matching the controlling award | Network Interconnection, Transport, Equipment, and Shared Facilities Agreement; S4/S10 | Interpretation | OPEN | Open-access/interconnection expectations; confirm scope in controlling award.