## Instructions
Closing Plan
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Parties: Lumbee Tribe of North Carolina (the “Lumbee Tribe”); LREMC Technologies, LLC d/b/a RIVR Tech (“RIVR Tech”); Lumbee River Electric Membership Corporation d/b/a Lumbee River EMC (“LREMC”), separate asset owner.
Closing and Implementation Plan
This workbook tracks every open item to closing, with an accountable owner, due date, dependency, and status.
How to use
• Filter the header row to focus on OPEN or BLOCKED items or a single owner.
• Due dates are placeholders until the closing calendar is fixed.
• Status values: OPEN, IN PROGRESS, BLOCKED, COMPLETE, N/A.
Reliance limits
• PRELIMINARY: no controlling award or source documents supplied.
• Confirming the controlling round/award is the gating item for most others.
Legend: | INPUT (edit these) | FORMULA (do not edit) | OUTPUT / RESULT

## Plan
Closing and Implementation Plan
PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW
Lumbee Tribe / RIVR Tech TBCP fiber package — Preliminary Draft v0.1
# | Open Item | Accountable Owner | Due Date | Dependency | Status
1 | Confirm controlling TBCP round and executed award | Tribe (grant lead) + Grant Counsel | [■ date] | Predecessor to nearly all definitive terms | OPEN
2 | Obtain Lumbee federal-recognition / eligibility opinion | Tribal Counsel | [■ date] | Confirm controlling round/award | OPEN
3 | Assemble procurement record supporting DEPC pricing | RIVR Tech + Tribe (grant lead) | [■ date] | Controlling award; procurement standards (200.317-.327) | OPEN
4 | Make contractor vs. subrecipient determination | Grant Counsel + Tribe | [■ date] | Award terms; 2 CFR 200.331 factors | OPEN
5 | Complete NEPA / NHPA §106 environmental & historic review | Environmental Consultant + Tribe (THPO/SHPO) | [■ date] | Route/scope (S2/S9); award | OPEN
6 | Secure land / ROW and BIA approvals where applicable | Tribal Counsel + Real Estate | [■ date] | Facility inventory (S9); NHPA clearance | OPEN
7 | Obtain LREMC board consent / joinder for LREMC Facilities | LREMC + Tribe + RIVR Tech | [■ date] | Facility inventory (S9) | OPEN
8 | Adopt limited sovereign-immunity waiver action | Tribal Council + Tribal Counsel | [■ date] | Waiver scope approved (G4) | OPEN
9 | Bind required insurance coverages | RIVR Tech (risk) + Broker | [■ date] | Insurance schedule (S12) finalized | OPEN
10 | Set per-Active-Subscriber amount and confirm characterization | Tribe + RIVR Tech (business) + Grant Counsel | [■ date] | Program-income determination (200.307) | OPEN
11 | Obtain NTIA/DOC written determinations (award, precedence, program income) | Tribe (grant lead) + Grant Counsel | [■ date] | Award confirmed; questions framed to NTIA | OPEN
12 | Issue segment Notice to Proceed (NTP) | Tribe (with RIVR Tech) | [■ date] | Environmental clearance; permits; approvals complete | OPEN
13 | Achieve segment acceptance (starts term clock) | RIVR Tech + Tribe (acceptance) | [■ date] | NTP; acceptance testing per S4 | OPEN
14 | Begin subscriber activation / provider-of-record operations | RIVR Tech | [■ date] | Segment acceptance; retail readiness (S7) | OPEN