PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW

00 · START HERE — DOCUMENT 02

Agreement Register and Signing Sequence

Coordinated TBCP Fiber Agreement Package — Lumbee Tribe of North Carolina and RIVR Tech

by and between

Lumbee Tribe of North Carolina

and

LREMC Technologies, LLC d/b/a RIVR Tech

Version:  Preliminary Draft v0.1

Version Date:  September 26, 2026

Document Status:  Working draft — not executed; not final legal advice

Program:  Tribal Broadband Connectivity Program (TBCP), National Telecommunications and Information Administration (NTIA)

CONFIDENTIAL – ATTORNEY WORK PRODUCT / SUBJECT TO COMMON-INTEREST PRIVILEGE

TABLE OF CONTENTS

(Right-click and choose “Update Field” in Microsoft Word to populate page numbers.)

# ARTICLE 1.  PURPOSE

This register lists each Definitive Agreement and Governance/Authorization document, its parties, purpose, place in the signing sequence, conditions precedent, and the Schedules it requires. Document names and Schedule numbers are used verbatim from the canonical register. [ATTORNEY REVIEW REQUIRED] [GRANT COMPLIANCE REVIEW REQUIRED]

| Document | Parties | Purpose | Seq # | Conditions Precedent | Required Schedules |
| --- | --- | --- | --- | --- | --- |
| Master TBCP Partnership and Implementation Agreement | Lumbee Tribe; RIVR Tech | Umbrella framework, shared definitions, precedence, governance | 3 | Governance authorizations executed; award confirmed | S1, S2, S3, S14 |
| Design, Engineering, Procurement, and Construction Agreement | Lumbee Tribe; RIVR Tech | Design, engineering, procurement, construction of Grant-Funded Assets | 4 | Master executed; environmental/NHPA clearances | S2, S4, S5 |
| Indefeasible Right of Use and Network Access Agreement | Lumbee Tribe; RIVR Tech | Grants RIVR Tech the IRU and network-access/retail rights | 5 | Master executed; asset register (S3) settled | S3, S10 |
| Network Interconnection, Transport, Equipment, and Shared Facilities Agreement | Lumbee Tribe; RIVR Tech | Interconnection, transport, equipment, shared facilities | 6 | IRU executed; demarcation (S4) fixed | S4, S9, S10 |
| Network Operations, Maintenance, and Lifecycle Agreement | Lumbee Tribe; RIVR Tech | Operations, maintenance, lifecycle, service levels | 7 | IRU executed; SLA schedule (S6) agreed | S6, S12 |
| Retail Customer Service, Billing, Collections, and Subscriber Revenue Agreement | Lumbee Tribe; RIVR Tech | Retail service, billing, collections, subscriber revenue | 8 | IRU executed; provider-of-record terms (S7) set | S7, S8 |
| Grant Finance, Reimbursement, Program Income, and Audit Agreement | Lumbee Tribe; RIVR Tech | Grant finance, reimbursement, program income, audit | 9 | Master executed; contractor/subrecipient determination | S1, S8 |
| Land, Easement, Right-of-Way, Pole, Site, Power, and Facility Instruments | Lumbee Tribe; RIVR Tech; LREMC (consent/joinder) | Land, easement, ROW, pole, site, power, facility instruments | 10 | LREMC consent; BIA/ROW approvals where applicable | S9, S14 |
| Data Privacy, Cybersecurity, Supply-Chain Risk, and Business Continuity Addendum | Lumbee Tribe; RIVR Tech | Data privacy, cybersecurity, supply-chain risk, continuity | 11 | Retail and O&M executed | S11 |
| Continuity, Step-In, Termination Assistance, and Transition Agreement | Lumbee Tribe; RIVR Tech | Continuity, step-in, termination assistance, transition | 12 | Master and O&M executed | S13 |
| Lumbee Tribal Council Resolution | Lumbee Tribe | Authorizes TBCP application/acceptance, asset ownership, execution of all Definitive Agreements, and signatories; sovereign-immunity waiver reserved | 1 | Award/round confirmed; eligibility opinion | S1 |
| RIVR Tech Member/Manager Authorization | RIVR Tech | RIVR Tech member/manager authorization of the transaction and signatories | 1 | Corporate records current | S1 |
| LREMC Consent and Joinder | LREMC | LREMC consent and joinder, limited to use of LREMC Facilities | 2 | Facility inventory (S9) identified | S9, S14 |
| Limited Waiver of Sovereign Immunity (bracketed alternatives — FOR COUNSEL) | Lumbee Tribe | Limited express waiver of sovereign immunity (bracketed alternatives — for counsel) | 2 | Scope of waiver approved by Tribal Council | S1, S13 |
| Tax, TERO, Permitting, and Regulatory Schedule | Lumbee Tribe; RIVR Tech | Tax, TERO, permitting, and regulatory requirements schedule (workbook) | 2 | Regulatory/TERO applicability confirmed by counsel | S8, S14 |
| Insurance Schedule | Lumbee Tribe; RIVR Tech | Insurance coverages, limits, and evidence schedule (workbook) | 2 | Coverages bound; certificates issued | S12 |
| Service Level Schedule | Lumbee Tribe; RIVR Tech | Service level targets and remedies schedule | 2 | SLA targets agreed with O&M | S6 |

# ARTICLE 2.  SIGNING-SEQUENCE NARRATIVE

The sequence numbers above group the closing into ordered stages. No commercial agreement is signed before the authority to sign it exists, and no segment goes live before the compliance predicates are satisfied.

## 2.1  Stage 1 — Resolutions and Authorizations First

The Lumbee Tribal Council Resolution (G1) and the RIVR Tech Member/Manager Authorization (G2) come first. These establish who may bind each party and confirm the threshold eligibility and award posture. [ATTORNEY REVIEW REQUIRED]

## 2.2  Stage 2 — Consents, Waiver, and Supporting Schedules

The LREMC Consent and Joinder (G3, limited to LREMC Facilities) and the Limited Waiver of Sovereign Immunity (bracketed alternatives — FOR COUNSEL) (G4) are settled next, because later agreements depend on LREMC Facility access and enforceable remedies. The supporting schedules — the Tax, TERO, Permitting, and Regulatory Schedule (G5), the Insurance Schedule (G6), and the Service Level Schedule (G7) — are finalized in this stage to feed the definitive agreements they support.

## 2.3  Stage 3 — Master Agreement

The Master TBCP Partnership and Implementation Agreement is executed next (sequence 3). It supplies the shared definitions, order of precedence, and governance that every downstream agreement incorporates.

## 2.4  Stage 4 — The Remaining Definitive Agreements

The DEPC, IRU, Interconnection, O&M, Retail, Grant Finance, Land Instruments, and Privacy/Cyber agreements are executed in dependency order (sequences 4–11): construction and the IRU precede operations, retail, and finance, which precede the privacy addendum.

## 2.5  Stage 5 — LREMC Consent Confirmed and Land Instruments

LREMC consent is confirmed in force and the Land Instruments (sequence 10) are recorded, together with any BIA/ROW approvals required where trust/restricted land is used or crossed. [GRANT COMPLIANCE REVIEW REQUIRED]

## 2.6  Stage 6 — Segment NTP, Acceptance, and Activation Last

Notice to Proceed, segment acceptance, and subscriber activation occur last, once the controlling award, eligibility, environmental/NHPA clearances, and all approvals are confirmed. The 20-year term runs from acceptance of each Network segment. [GRANT COMPLIANCE REVIEW REQUIRED]

PRELIMINARY DRAFT – NO CONTROLLING TBCP AWARD OR SOURCE DOCUMENTS SUPPLIED – PROVISIONAL BASELINE: MARCH 2024 AMENDED ROUND 2 NOFO – SUBJECT TO LEGAL, GRANT AND FINANCIAL REVIEW

This document is a preliminary working draft prepared for discussion only. It is not final legal, grant, or financial advice and creates no binding obligation on any party. No controlling TBCP award, Notice of Funding Opportunity in executed form, Specific Award Conditions, or other source documents were supplied; the provisional baseline is the March 2024 amended Round 2 NOFO, and the controlling round and executed award must be confirmed before any provision is finalized. All party names, defined terms, economics, dates, and citations are subject to legal, grant, and financial review. Capitalized terms used and not otherwise defined have the meanings given in Article 2 (Definitions) of the Master TBCP Partnership and Implementation Agreement, the single shared definitions source for the package. Nothing herein should be relied upon as fact where marked as a placeholder or flagged for review.

CONFIDENTIAL – ATTORNEY WORK PRODUCT / SUBJECT TO COMMON-INTEREST PRIVILEGE