RIVR TECH

LREMC Technologies, LLC d/b/a RIVR Tech

Implementation Roadmap

RIVR Tech Home Protection — 30/60/90-Day Plan

Operational Rollout, Approvals, and Pilot Design

| Document Version | v1.0 (Draft for Executive Review) |
| --- | --- |
| Date | 2026-07-29 |
| Effective Date | [EFFECTIVE DATE — TO BE SET BY EXECUTIVE TEAM] |
| Prepared By | Finance / COO / Customer-Experience Working Team |
| Region | Broadband services in southeastern North Carolina |

INTERNAL DRAFT FOR EXECUTIVE REVIEW — NOT LEGAL ADVICE. Contains recommendations and labeled assumptions requiring legal, regulatory, accounting, and insurance review before adoption.

Table of Contents

Right-click and choose 'Update Field' to build the table of contents.

# 1. Phased Timeline

| Phase | Focus |
| --- | --- |
| Days 1–30 | Design & approvals: coverage tiers, pricing, legal/tax review, NISC billing-code and product/service-code setup, eligibility rules, terms & conditions. |
| Days 31–60 | Build & train: billing configuration, work-order/trouble-ticket reason codes, technician findings + photo documentation, dispute/refund procedures, employee + MSR training, website/T&C/bill messages/FAQ. |
| Days 61–90 | Pilot & review: limited-market pilot, enrollment and opt-in flows, quality-control audits, monthly reporting, post-pilot go/no-go. |

# 2. Workstream Detail

| Workstream | Key Tasks | Owner | Approval |
| --- | --- | --- | --- |
| Billing / NISC | Product & service codes, line-item name, tax review, adjustments | Billing / IT | CFO / Tax |
| Legal / Regulatory | Negative-option, Lifeline, naming, NC consumer protection, T&C | General Counsel | CEO |
| Operations | Work-order coding, reason codes, tech findings, photos, materials tracking | COO / Field Ops | COO |
| Customer Experience | Scripts, dispute/appeal, refunds, QA audits | CX Lead | COO |
| Marketing | Website, bill messages, email, direct mail, FAQ | Marketing | Legal |
| Training | Technician, support, sales, MSR training | Enablement | COO |
| Finance | Model validation, pilot metrics, reporting | Finance | CFO |

# 3. Required Approvals & Decision Gates

Legal opinion on negative-option/opt-out billing and Lifeline/Tribal Lifeline treatment.

Tax determination on the plan charge.

Executive approval of price, coverage tier, and enrollment structure.

NISC configuration tested in a non-production environment.

Pilot success criteria met before system-wide launch.

# 4. Pilot Design (recommended)

Scope: one or two representative service areas; voluntary opt-in only.

Duration: 90 days.

Enrollment offer: at installation and after first chargeable call.

Metrics: enrollment take-rate, utilization %, cost per covered call, complaints, churn, dispute rate, coding accuracy.

Success thresholds (editable): take-rate ≥ 25%, utilization ≤ 20%, complaint rate flat, churn increase ≤ 0.5%.

Decision: go/no-go and price/tier adjustment after review.

# 5. Post-Launch Review

Review at 30, 60, and 90 days post-launch: financial performance vs. model, utilization, complaints and disputes, churn, and coding accuracy. Adjust price, coverage, or exemptions as needed. Report monthly to executives.

# 6. Naming & Billing Display

Recommended customer-facing name: RIVR Tech Home Protection (optional). Display as a clearly labeled optional line item. Do NOT describe the charge as a government fee, tax, mandatory regulatory fee, or network fee unless legally accurate.

LEGAL / REGULATORY REVIEW Billing display, naming, and disclosures require legal and billing review.

# 7. Data to Collect Before Final Approval

Actual 12-month residential trouble-call volume and % customer-caused.

True fully loaded cost per truck roll (labor, vehicle, fuel, materials, repeat rate).

Baseline residential churn and any prior fee-change churn experience.

Count of Lifeline / Tribal Lifeline / low-income residential accounts.

Count of bulk / managed-property and renter accounts.

NISC billing-code and tax-configuration effort/quote.

Real collection and bad-debt experience on customer charges.

Customer willingness-to-pay / survey for a protection plan.

Legal opinion on negative-option/opt-out billing in NC.

Expected enrollment take-rate from a pilot.