## 90-Day Tracker
RIVR Tech — 90-Day Implementation Tracker
Five phases from policy to full billing and optimization
v1.0 (Draft for Executive Review) ¦ 2026-07-20 ¦ LREMC Technologies, LLC d/b/a RIVR Tech ¦ NOT LEGAL ADVICE
LEGEND: | User input | Calculated | Recommended | Review / warning
Task | Workstream | Phase | Owner | Start | Due | Dependency | Status | Risk | Mitigation | Exec Decision Required
Finalize policy draft | Policy | 1 | Policy Lead | Day 1 | Day 10 | - | Not started | Med | Reuse this draft; legal review | Yes — approve posture
Validate financial model with real data | Finance | 1 | Finance | Day 1 | Day 12 | Data pull | Not started | Med | Replace 10 assumptions | Yes — approve fees
Legal & regulatory review (NC) | Legal | 1 | General Counsel | Day 3 | Day 20 | Policy draft | Not started | High | Engage counsel early | Yes — scope
Insurance characterization (plan) | Legal | 1 | GC / Insurance | Day 3 | Day 20 | Plan design | Not started | High | Confirm not insurance | Yes — plan launch
Design ticket & billing codes | Systems | 1 | IT / Billing | Day 5 | Day 25 | Policy | Not started | Med | Use code list in SOP | No
Configure billing system | Systems | 1 | IT / Billing | Day 15 | Day 35 | Codes | Not started | High | Vendor quote; test env | No
Build portal / e-acknowledgment | Systems | 1 | IT | Day 15 | Day 40 | Legal (E-SIGN) | Not started | Med | UETA/E-SIGN review | No
Develop training materials | Training | 2 | Enablement | Day 20 | Day 40 | Policy final | Not started | Low | Deck + QRG + assessment ready | No
Train all employee roles | Training | 2 | Enablement | Day 40 | Day 55 | Materials | Not started | Med | Passing score 80% | No
Launch 60-day customer education | Comms | 2 | Marketing | Day 35 | Day 95 | Legal wording | Not started | Med | Warm, local messaging | No
Publish website policy & FAQs | Comms | 2 | Marketing | Day 40 | Day 50 | Legal wording | Not started | Low | Use comms package | No
Begin 30-day warning-only period | Ops | 3 | Support Ops | Day 55 | Day 85 | Training done | Not started | Med | Disclose, don't bill | Yes — grace period
Apply first-incident courtesy waivers | Ops | 3 | Supervisors | Day 55 | Ongoing | Warning period | Not started | Low | Track waivers | No
Dry-run dispute & waiver workflows | CX | 3 | CX Lead | Day 60 | Day 80 | Systems | Not started | Med | Simulate disputes | No
Go-live: full billing implementation | Ops | 4 | Support Ops | Day 85 | Day 90 | All above | Not started | High | Exec sign-off gate | Yes — go/no-go
Monitor KPIs & coding accuracy | Quality | 4 | QA | Day 85 | Ongoing | Go-live | Not started | Med | KPI dashboard | No
30-day post-launch review | Exec | 5 | COO | Day 115 | Day 120 | Go-live | Not started | Low | Optimize fees/waivers | Yes — adjust
Optimize remote-resolution playbooks | Ops | 5 | Support Ops | Day 100 | Ongoing | KPIs | Not started | Low | Raise deflection | No

## Phase Overview
RIVR Tech — Implementation Phases
Five-phase rollout
v1.0 (Draft for Executive Review) ¦ 2026-07-20 ¦ LREMC Technologies, LLC d/b/a RIVR Tech ¦ NOT LEGAL ADVICE
Phase | Focus | Window
Phase 1 | Policy, financial validation, legal review, and system design | Days 1–40
Phase 2 | Employee training and customer education | Days 20–95
Phase 3 | 30-day warning and courtesy-waiver period | Days 55–85
Phase 4 | Full billing implementation | Days 85–90
Phase 5 | Performance review and optimization | Days 90–120+