## Cover
RIVR Tech — Phase 1 Onboarding Tracker
ETC approved → USAC onboarding (30/60/90-day plan) (Deliverable 14)
LREMC Technologies, LLC d/b/a RIVR Tech
NCUC ETC order date (Day 0): | 2026-09-28 | EDIT THIS to the actual order date — every target date recalculates from it. [CONFIRM]
Owner: |  | Program Owner (with Executive Sponsor & Compliance Officer)
Version: |  | v0.1 — Phase 1 kickoff
Source basis: |  | 00_Regulatory_Source_Register.md (SR-6 onboarding sequence)
Companions: |  | 07 Compliance Checklist · 08 Roadmap/RACI · 12 Readiness Scorecard · 13 Open Issues
CRITICAL — NCUC/Lifeline approval does NOT authorize the enhanced $34.25 Tribal benefit based on Lumbee membership. Enhanced support requires the customer's principal residence to be on qualifying Tribal lands (47 C.F.R. §54.400(e)), verified per-address via USAC's tool. Operate with ZERO enhanced-Tribal subscribers until a written USAC/legal determination confirms otherwise (Open Issue ISS-01).
Legend:
INPUT — edit me
PLACEHOLDER — replace w/ confirmed figure
PROGRAM CONSTANT — re-verify each year
CALCULATED — do not edit

## Critical Path 0-90d
USAC Onboarding — Critical Path
Target date = Day 0 + offset (auto from Cover). Do in order; ⏱ = long pole, start Day 1.
# | Task | Window | Owner | Depends on | Offset (days) | Target date | Status | Evidence / ID captured | Risk if it slips
1 | Obtain & file the final NCUC ETC order; extract service area, effective date, conditions | 0-30 | Reg. Counsel | — | 3 |  |  | Order PDF on file | Everything downstream stalls
2 | ⏱ Start SAM.gov registration: UEI + active bank account (same TIN as FRN) | 0-30 | Finance | — | 2 |  |  | UEI issued; bank verified | ~6-wk long pole; blocks disbursement
3 | Obtain FCC Registration Number (FRN) via CORES (if not held) | 0-30 | Finance | — | 5 |  |  | FRN (10-digit) | Blocks SAM/498
4 | Request Study Area Code (SAC) from USAC (email order to LifelineProgram@usac.org) | 0-30 | Compliance | NCUC order | 14 |  |  | SAC assigned | Blocks 498/claims
5 | Adopt written WFA policy, record-retention & privacy controls; exec sign-off | 0-30 | Compliance/Exec | — | 21 |  |  | Signed policies | Audit exposure
6 | Enroll enrollment reps in RAD → obtain Rep IDs (LifelineRAD.org) | 0-30 | Compliance | — | 21 |  |  | Rep IDs list | Cannot enroll without them
7 | File FCC Form 498 → obtain 498 ID; Company Officer certifies (14-day window) | 30-60 | Finance/Officer | SAM UEI + SAC | 42 |  |  | 498 ID (SPIN) | Blocks reimbursement
8 | Assign 497 Officer + ETC Administrator roles in USAC One Portal | 30-60 | Finance/Compliance | 498 ID | 45 |  |  | Role confirmations | Blocks NV/NLAD/LCS setup
9 | Provision National Verifier access + user roles (One Portal) | 30-60 | Compliance/IT | ETC Admin + Rep IDs | 50 |  |  | NV access confirmed | Cannot verify eligibility
10 | Provision NLAD access + roles; test enrollment upload | 30-60 | Compliance/IT | ETC Admin + Rep IDs | 52 |  |  | NLAD access confirmed | Cannot enroll subscribers
11 | Provision LCS access for monthly claims | 30-60 | Finance | 497 Officer | 55 |  |  | LCS access confirmed | Cannot claim reimbursement
12 | Complete NISC config + end-to-end test (codes, tax, GL, pass-through) | 30-60 | Billing/IT | Rate/credit codes | 58 |  |  | Test results signed | Billing errors at launch
13 | Complete employee training (RAD reps trained before enrolling) | 30-60 | Compliance/Training | SOPs, Rep IDs | 56 |  |  | Training records | Non-compliant enrollments
14 | Run controlled pilot: enroll→NV→NLAD→bill→LCS→3-way reconcile (≤25-50) | 60-90 | Cross-functional | All access live | 75 |  |  | Clean 3-way reconciliation | Scale-up errors
15 | Validate customer notices & experience during pilot | 60-90 | MSR/Marketing | Pilot roster | 78 |  |  | Notice log | Poor CX at launch
16 | Readiness Scorecard review → GO/NO-GO gate (Deliverable 12) | 60-90 | Exec Sponsor | Pilot pass | 85 |  |  | Signed scorecard (all gates green) | Launch on shaky footing
17 | Public launch across approved ETC service area (coordinated RIVR + Lumbee comms) | 60-90 | Program Owner/Marketing | GO decision | 90 |  |  | Launch live | —

## Parallel Workstreams
Parallel Workstreams (don't wait for onboarding to finish)
Workstream | Action | Owner | Offset | Target date | Status
Pricing & plan | Confirm RIVR price sheet; lock Senior 100/100 design (Alt D: $10 net) | Product/Finance | 20
Tax | Obtain tax-advisor opinion on taxable components; no 'plus tax' until back | Tax Advisor/CFO | 25
NISC billing | Build rate/credit codes, tax config, separate-GL accounts, bill text | Billing/IT | 40
Policies | Finalize WFA, record-retention, privacy/data-security controls | Compliance | 21
Training | Build & deliver role modules; prohibited-statements drill | Compliance/Training | 50
Comms | Finalize website/FAQ/letters/scripts; keep guardrails; publicize Lifeline (§54.405(b)) | Marketing/Compliance | 60
Lumbee MOU | Execute MOU if Tribe funds a discount / runs membership verification | Exec Sponsor/Legal | 60
Tribal-lands determination | Obtain written USAC/legal determination (ISS-01) BEFORE any enhanced claim | Reg. Counsel/USAC | 30

## Decisions Due
Executive Decisions Due (from 01 §11 / 13)
Ref | Decision | Recommended | Decision-maker | Offset | Target date
ISS-14 | Enhanced Tribal legal determination | Obtain written USAC/legal determination; assume 0 until confirmed | Reg. Counsel + USAC | 25
ISS-02 | Tax treatment / 'plus tax' | Obtain tax opinion; no 'plus tax' until confirmed | Tax Advisor + CFO | 25
ISS-03 | Senior eligibility age | 62 | Exec Sponsor | 15
ISS-04 | $10 retail vs net | NET after subsidies (Alt D) | Exec Sponsor + CFO | 15
ISS-05 | Company-funded discount for non-Lifeline seniors | Yes, capped | CFO | 15
ISS-07 | Equipment & installation charges | Waive/fold equipment; free install | Product + CFO | 15
ISS-06 | Lumbee Tribe additional funding | Pursue via MOU; base case $0 | Exec Sponsor + Tribe | 45
ISS-13 | Pilot size & launch date | ≤25-50 pilot; launch after 3-way recon passes | Program Owner | 60

## Milestones
30 / 60 / 90-Day Milestone Gates
Milestone | Target date | Definition of done
Day 30 |  | Order filed; SAM.gov in flight; FRN + SAC requested; RAD Rep IDs; WFA/privacy policies signed; Tribal-lands determination requested
Day 60 |  | 498 ID + officer roles live; NV/NLAD/LCS access provisioned; NISC configured & tested; training complete; price sheet + tax opinion in hand
Day 90 |  | Pilot passed with clean 3-way reconciliation; Readiness Scorecard all-green; public launch across ETC service area
Dates auto-calc from the NCUC order date on the Cover tab. These are planning targets; the SAM.gov (~6 wk) and SAC turnaround are the two USAC-controlled timings to watch.