## Cover
RIVR Tech — Lifeline & Lumbee Broadband Affordability
Compliance & Audit Checklist (Deliverable 07)
LREMC Technologies, LLC d/b/a RIVR Tech
Owner: Program Owner + noted functional owners
Version: v0.1 — DRAFT (build phase, ETC application pending)
Source basis: 00_Regulatory_Source_Register.md (refs 'SR-x.y')
Status: PRE-DECISION. Confirm all placeholder figures before reliance.
Every row cites the governing rule (SR ref). 'Status' and 'Evidence' are for the Compliance Officer to complete. NO customer may be enrolled, and NO reimbursement claimed, until the onboarding rows are Complete and the final NCUC ETC order is in hand.
Legend:
INPUT — edit me
PLACEHOLDER — replace w/ confirmed figure
PROGRAM CONSTANT — re-verify each year
CALCULATED — do not edit

## Checklist
Lifeline Compliance & Audit Checklist
# | Requirement | Citation (SR ref) | Owner | Status | Evidence / doc link | Due
A. ETC designation & USAC onboarding
1 | Final NCUC ETC designation order received | SR-6.1/SR-7.4 | Reg. Counsel
2 | Confirmed ETC service area documented | SR-6.1/SR-7.1 | Reg. Counsel
3 | FCC Registration Number (FRN) via CORES | SR-6.2 | Finance
4 | SAM.gov UEI active + bank account | SR-6.3 | Finance
5 | Study Area Code (SAC) issued by USAC | SR-6.4 | Compliance
6 | 498 ID / FCC Form 498 filed & officer-certified | SR-6.5 | Finance/Officer
7 | RAD Rep IDs for all enrollment reps | SR-6.6 | Compliance
8 | National Verifier access + roles provisioned | SR-6.7 | Compliance/IT
9 | NLAD access + roles provisioned | SR-6.7 | Compliance/IT
10 | LCS access + 497 Officer assigned | SR-6.8 | Finance/Officer
B. Eligibility & enrollment
11 | National Verifier approval BEFORE every NLAD enroll | SR-3.1 | MSR/Compliance
12 | One-per-household worksheet where applicable | SR-1.8 | MSR
13 | Income (135% FPG) / program eligibility captured | SR-1.4/1.6 | MSR
14 | Consent + benefit-transfer consent on file | SR-3.6 | MSR
15 | Tribal-lands per-address verification via USAC tool | SR-4.4 | Compliance
16 | Enhanced $25 claimed ONLY for verified Tribal-lands addr | SR-4.2/5.5 | Compliance
17 | NLAD updated within 10 business days of changes | SR-3.2 | Billing
C. Billing & pass-through
18 | Full Lifeline support passed through on the bill | SR-6.8 | Billing
19 | Separate GL for Lifeline / grant / RIVR / Tribe funds | SR-10.2 | Accounting
20 | Min service standards met (25/3, 1280GB) — 100/100 OK | SR-2.1/2.2 | Network
21 | No 'plus tax' advertised until tax advisor confirms | SR-9.9 | Marketing/Tax
D. Recertification & de-enrollment
22 | Annual recertification process (60-day window) | SR-3.3 | Compliance
23 | Non-usage rule handling (if $0-fee applies) | SR-3.4 | Billing/Legal
24 | De-enrollment on failure/ineligibility/duplicate | SR-3.5 | Compliance
E. Reporting & records
25 | FCC Form 481 filed by July 1 (confirm year deadline) | SR-6.9 | Compliance
26 | FCC Form 555 filed by Jan 31 (+ECFS 14-171) | SR-6.10 | Compliance
27 | Record retention ≥3 yrs / duration of service | SR-6.11 | Compliance
28 | Lifeline advertising / publicizing availability | SR-6.12 | Marketing
29 | NC reporting to NCUC as required | SR-7.1 | Reg. Counsel
F. Waste, fraud & abuse / audit readiness
30 | Written WFA policy adopted & executive-signed | SR-6.* | Compliance/Exec
31 | No duplicate benefits; NLAD de-dup enforced | SR-1.8/3.2 | Compliance
32 | Claim only for properly NLAD-enrolled subscribers | SR-6.8 | Finance
33 | Audit trail / logs retained; access role-based | SR-6.11 | IT/Compliance
34 | Officer certifications on 481/555/LCS | SR-6.8/6.9/6.10 | Officer