## Cover
RIVR Tech — Lifeline & Lumbee Broadband Affordability
Implementation Roadmap & RACI (Deliverable 08)
LREMC Technologies, LLC d/b/a RIVR Tech
Owner: Program Owner + noted functional owners
Version: v0.1 — DRAFT (build phase, ETC application pending)
Source basis: 00_Regulatory_Source_Register.md (refs 'SR-x.y')
Status: PRE-DECISION. Confirm all placeholder figures before reliance.
Phased plan (0–4). No public marketing as an approved Lifeline provider until Phase 1 completes (final ETC order + USAC onboarding). Pilot (Phase 2) precedes public launch (Phase 3).
Legend:
INPUT — edit me
PLACEHOLDER — replace w/ confirmed figure
PROGRAM CONSTANT — re-verify each year
CALCULATED — do not edit

## Roadmap
Phased Implementation Roadmap
Dates are relative placeholders — set absolute dates once the ETC order date is known.
Task | Owner | Dependency | Start | Target | Approval | Evidence of completion | Risk if delayed | Status
PHASE 0 — ETC application pending (now)
Complete regulatory research & source register | Reg. Counsel | — | T-0 | T+2w | Program Owner | Signed source register | Design on wrong assumptions
Obtain Lumbee Tribal-lands legal/USAC determination | Reg. Counsel | Research | T-0 | T+8w | Exec Sponsor | Written determination | Mis-set enhanced benefit
Confirm RIVR price sheet (all tiers/equip/voice) | Product/Finance | — | T-0 | T+3w | CFO | Confirmed price sheet | Bad financial model
Financial model + scenarios | Finance | Prices | T+3w | T+6w | CFO | Approved model | Unclear viability
Draft policies/SOPs/NISC spec | Program Owner | Research | T-0 | T+8w | Compliance | Draft docs | Slow launch
Lumbee MOU discussions (no obligations yet) | Exec Sponsor | — | T-0 | T+10w | Board | Term sheet | No partnership
PHASE 1 — ETC approval & USAC onboarding
Receive final NCUC ETC order | Reg. Counsel | NCUC | T+Xw | — | — | Order on file | Cannot proceed
FRN, SAM.gov UEI, SAC, 498 ID | Finance | ETC order | +1w | +6w | Officer | System IDs | No reimbursement
RAD Rep IDs; NV/NLAD/LCS access | Compliance/IT | 498 ID | +2w | +6w | Compliance | Access confirmed | Cannot enroll
NISC configuration + test | Billing/IT | Spec | +2w | +8w | Compliance | Test results | Billing errors
Employee training complete | Training | SOPs | +4w | +9w | Compliance | Training records | Non-compliant reps
PHASE 2 — Controlled pilot
Select ≤25–50 existing customers | Program Owner | Phase 1 | +9w | +10w | Compliance | Pilot roster | Untested process
Run enrollment → NLAD → bill → LCS → reconcile | Cross-functional | Pilot roster | +10w | +14w | Compliance | 3-way recon | Scale errors
Validate notices & customer experience | MSR/Marketing | Pilot | +10w | +14w | Program Owner | Notice log | Poor CX
PHASE 3 — Public launch
Coordinated RIVR + Lumbee comms | Marketing | Pilot pass | +14w | +16w | Exec/Tribe | Launch assets | Weak uptake
Open enrollment across ETC area | MSR | Launch | +16w | — | Program Owner | Enrollment vol. | —
PHASE 4 — Stabilization
30/60/90-day reviews | Program Owner | Launch | +20w | +30w | Exec Sponsor | Review memos | Unfixed issues
Correct enrollment/billing/claims/training | Cross-functional | Reviews | +20w | +30w | Compliance | Corrective log | Recurring errors

## RACI
RACI Matrix (R=Responsible A=Accountable C=Consulted I=Informed)
Task / workstream | Exec Sponsor | Program Owner | Compliance | Reg. Counsel | Finance | Accounting | Billing | IT | MSR/CS | Sales | Marketing | Network | Lumbee Tribe | Internal Audit
ETC designation & regulatory filings | I | R | C | A | I
USAC onboarding (FRN/SAC/498/RAD) |  | I | R |  | A |  |  | C
Eligibility determination (NV) |  |  | A | C |  |  |  |  | R |  |  |  |  | I
Tribal-lands verification | I |  | A | R |  |  |  |  | C |  |  |  | C
Enrollment & NLAD |  |  | A |  |  |  | C | I | R
NISC billing configuration |  |  | C |  | C |  | A | R
Monthly LCS claim & reconciliation |  |  | C |  | A | R | [7 empty] | I
Recertification & de-enrollment |  |  | A |  |  |  | C |  | R
Privacy & data security |  |  | R | C |  |  |  | A | [5 empty] | I
Financial model & budget | C | I |  |  | A | R
Customer communications |  |  | C | [5 empty] | R |  | A |  | C
Employee training |  | R | A | [5 empty] | I | I
Lumbee partnership & MOU | A | R |  | C | [8 empty] | C
Field install / service | [7 empty] | R | C |  |  | A
Internal audit & WFA controls | I |  | R | [10 empty] | A