## Cover
RIVR Tech — Lifeline & Lumbee Broadband Affordability
Open Issues & Legal Decisions Log (Deliverable 13)
LREMC Technologies, LLC d/b/a RIVR Tech
Owner: Program Owner + noted functional owners
Version: v0.1 — DRAFT (build phase, ETC application pending)
Source basis: 00_Regulatory_Source_Register.md (refs 'SR-x.y')
Status: PRE-DECISION. Confirm all placeholder figures before reliance.
Single source of truth for unresolved questions. Each has a recommended decision, rationale, named decision-maker, and required-by date. Enhanced-Tribal eligibility (ISS-01) is the highest-severity item and gates any enhanced-benefit claim.
Legend:
INPUT — edit me
PLACEHOLDER — replace w/ confirmed figure
PROGRAM CONSTANT — re-verify each year
CALCULATED — do not edit

## Open Issues
Open Issues & Legal Decisions Log
ID | Issue / decision | Sev | Recommended decision | Rationale | Decision-maker | Required by | Status
ISS-01 | Do any Lumbee lands qualify as FCC 'Tribal lands' (§54.400(e)/§54.412)? | HIGH | Assume NO qualifying Tribal lands; set enhanced $25 to 0 subs until written USAC/legal determination confirms otherwise. | No reservation/trust land; four-county service area ≠ Tribal lands; no §54.412 designation (SR-4/SR-5). | Reg. Counsel + USAC/FCC ONAP | Before enroll | Open
ISS-02 | Which Senior-plan components are taxable? | HIGH | Tax advisor written opinion; do not advertise 'plus tax' until received (broadband access non-taxable per ITFA). | NC taxes voice/equip; ITFA bars internet-access tax; managed Wi-Fi open (SR-9). | Tax Advisor + CFO | Before launch | Open
ISS-03 | Senior eligibility age: 60 / 62 / 65? | MED | Recommend 62 (Social Security early-retirement anchor; balances reach vs. exposure). | 65 = fewer, safer; 60 = broadest, costliest; 62 = middle (see Exec Plan). | Exec Sponsor | Phase 0 end | Open
ISS-04 | Is $10 the retail price or net-after-subsidy? | HIGH | Recommend Alternative D: $10 is the NET target after Lifeline + defined top-up (retail stays list). | Avoids over-recovery on tribal; simplest NISC admin; protects non-LL seniors (SR-1/Fin Model). | Exec Sponsor + CFO | Phase 0 end | Open
ISS-05 | Do non-Lifeline seniors get a company-funded discount? | MED | Yes under Alt D, capped; model exposure; revisit if uptake high. | Equity of a 'senior plan'; but full company cost w/o USAC offset. | CFO | Phase 0 end | Open
ISS-06 | Does the Lumbee Tribe contribute funding? | MED | Pursue via MOU but do not assume; model with $0 Tribe funding as base case. | Separate accounting required; no commitment yet (SR-10). | Exec Sponsor + Tribe | Phase 1 | Open
ISS-07 | Equipment & install charges for the Senior plan? | MED | Recommend waive/lower equipment to protect the $10 target; confirm tax. | $5/mo router would break the $10 target unless folded in (SR-8.4). | Product + CFO | Phase 0 end | Open
ISS-08 | Can voice be bundled? | LOW | Offer voice as OPTIONAL add-on; keep out of the $10 broadband target; disclose voice taxes/911/USF. | Voice is taxable & assessed; Lifeline min-standard is broadband (SR-2/SR-9). | Product + Tax | Phase 1 | Open
ISS-09 | Non-usage rule applicability with a $10 charge? | MED | Confirm with counsel; if a >$0 fee applies, the 30/15-day non-usage rule likely does not. | Rule targets $0-fee services (SR-3.4). | Reg. Counsel | Phase 1 | Open
ISS-10 | NCUC ETC docket status for LREMC/RIVR? | HIGH | Confirm docket number & status via NCUC portal/staff; track to final order. | Not found via search (SR-7.3). | Reg. Counsel | Phase 0 | Open
ISS-11 | TBCP/grant funds for recurring bills? | MED | Do NOT use for recurring consumer subsidy unless award terms expressly allow; keep separate GL. | Grant terms govern; commingling risk (SR-10). | CFO + Reg. Counsel | Before use | Open
ISS-12 | Membership verification method w/ the Tribe (privacy)? | MED | Tribe-run attestation / hashed match; NO transfer of full tribal roll to RIVR. | Data minimization; privacy (see MOU & Privacy sec). | Program Owner + Tribe | Phase 1 | Open
ISS-13 | Pilot size & launch date? | LOW | ≤25–50 pilot customers; set launch after pilot 3-way recon passes. | De-risk before scale. | Program Owner | Phase 2 | Open
ISS-14 | Branding / Tribe name & logo use approval? | LOW | Written Tribe approval before any joint asset uses name/logo. | Sovereignty & brand control (MOU). | Marketing + Tribe | Phase 3 | Open